## Product backlog
Product backlog
Start date | 2020-10-24
End date | 2021-10-24
Duration (days) | 365
SubSystem | Actor | Epic | User Story |  | Hour | Sprint | Status
User System | Manager | Ingredients Management | ListView Ingridients | ListView | 2 | 1 | Done
|  |  |  | Search ingridients | 1 |  | Done
|  |  | Insert Ingridients |  | 3 | 2 | Not started yet
|  |  | Delete Ingridients |  | 3 | 2 | Not started yet
|  |  | Update Ingridients |  | 3 | 1 | Not started yet
|  | Employees Management | ListView Employee | ListView | 2 | 1 | Not started yet
|  |  |  | Search employees | 1 |  | Not started yet
|  |  | Insert employees |  | 3 |  | Not started yet
|  |  | Update employees |  | 3 |  | Not started yet
|  |  | Delete employees |  | 3 | 1 | Not started yet
| Admin | Account Management | ListView Account | ListView | 3 | 2 | Not started yet
|  |  |  | Search Account | 3 | 2 | Not started yet
|  |  | Update Account | Add Account | 3 | 2 | Not started yet
|  |  |  | Remove Account | 3 |  | Not started yet
|  |  | Delete Account |  | 3 | 3 | Not started yet

## Master shedule
Master schedule (10/24/2020 - 10/24/2021)
| Start date | End date | Duration (days)
Sprint 1 | 2020-10-24 | 2020-11-07 | 14
Sprint 2 | 2020-11-10 | 2020-11-21 | 11
Sprint 3 |  |  | 0
Sprint 4 |  |  | 0
Sprint 5 |  |  | 0

## Sprint 1
Sprint 1 (10/24/2020-11/07/2020)
Start date | 2020-10-24
End date | 2020-11-07
Duration (days) | 14
Number of Story | 21
Number of Points | 84
SubSystem | Actor | Epic | User Story |  |  | Point | Task owner | Status
User System | Manager | Quản lý Câu hỏi - Đáp án | View list Câu hỏi | View list |  | 3 | Lê Hữu Đoàn | Done
|  |  |  | Search câu hỏi |  | 3 |  | Done
|  |  |  | Filter danh sách câu hỏi |  | 3 |  | In progress
|  |  |  | Sort danh sách câu hỏi |  | 3 |  | Not started yet
|  |  | Tạo câu hỏi | Backend |  | 8 | Nguyễn Ngọc Duy | Not started yet
|  |  |  | UX/UI |  | 13 | Nguyễn Thị Giang | Not started yet
|  |  | Delete Question |  |  | 3 | Nguyễn Huy Anh | Not started yet
|  | Quản lý Category Câu hỏi | Update category câu hỏi |  |  | 3 | Vũ Đình Hào | Not started yet
|  |  | Delete category câu hỏi |  |  | 3 |  | Not started yet
|  | Quản lý Đề thi | Tạo Đề thi |  |  | 5 | Nguyễn Thị Vân Anh | Not started yet
|  |  | Hiển thị danh sách đề thi | View list |  | 3 | Nguyễn Văn Đông | Not started yet
|  |  |  | Sort đề thi |  | 3 |  | Not started yet
|  |  |  | Search đề thi |  | 3 |  | Not started yet
|  |  |  | Filter đề thi |  | 3 |  | Not started yet
|  |  | Delete Đề thi |  |  | 3 | Vũ Đình Hào | Not started yet
| Admin | Quản lý Tài Khoản | Hiển thị danh sách tài khoản | Filter tài khoản |  | 3 | Nguyễn Huy Anh | Not started yet
|  | Quản lý nhóm Tài Khoản | View List nhóm tài khoản | Filter nhóm tài khoản |  | 3 | Vũ Đình Hào | Not started yet
|  |  | View details nhóm tài khoản | Filter tài khoản trong nhóm |  | 3 | Nguyễn Huy Anh | Not started yet
|  |  | Update nhóm tài khoản | Update Account trong nhóm tài khoản | Add Account | 5 | Nguyễn Văn Anh Ngọc | Not started yet
[5 empty] | Remove Account | 5 |  | Not started yet
|  |  | Delete nhóm tài khoản |  |  | 3 | Nguyễn Huy Anh | Not started yet